## Sheet1
King's Quest Assessment Task Gantt Chart
Week |  |  | Week 6 ¦ June 3rd | [6 empty] | Week 7 ¦ June 10th | [6 empty] | Week 8 ¦ June 17th | [6 empty] | Week 9 ¦ June 24th | [6 empty] | Holidays ¦ July 1st | [6 empty] | Holidays ¦ July 8th | [6 empty] | Holidays ¦ July 15th | [6 empty] | Week 1 ¦ July 22nd
Dates |  |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Days |  |  | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri
Key: | Projected:
Actual:
Task | Start | End
Video | 2024-07-23 | 2024-07-24 | bar: Week 1 ¦ July 22nd 23 Tues to Week 1 ¦ July 22nd 25 Thur
Video
Setup Project Files | 2024-06-03 | 2024-06-19 | bar: Week 6 ¦ June 3rd 3 Mon to Week 6 ¦ June 3rd 9 Sun
Set Up Files
Documentation
Gantt Chart | 2024-06-04 | 2024-07-24
Gantt
Context Diagram | 2024-06-08 | 2024-07-23 | bar: Week 6 ¦ June 3rd 8 Sat to Holidays ¦ July 15th 19 Fri
Context
DFD | 2024-06-08 | 2024-07-23 | bar: Week 6 ¦ June 3rd 8 Sat to Week 1 ¦ July 22nd 22 Mon
DFD
UML (Class) | 2024-06-08 | 2024-07-23 | bar: Week 6 ¦ June 3rd 8 Sat to Holidays ¦ July 8th 14 Sun
UML
Logbook | 2024-07-04 | 2024-07-24 | bar: Holidays ¦ July 1st 4 Thur to Week 1 ¦ July 22nd 24 Wed
Logbook
Health Bar
Health bar appears on screen | 2024-06-19 | 2024-07-04 | bar: Week 8 ¦ June 17th 19 Wed to Week 9 ¦ June 24th 26 Wed
Appear
Set to player health | 2024-06-25 | 2024-07-04 | bar: Week 9 ¦ June 24th 25 Tues to Holidays ¦ July 1st 7 Sun
Player hp
Set to enemy health | 2024-07-04 | 2024-07-04 | bar: Holidays ¦ July 1st 4 Thur to Holidays ¦ July 1st 5 Fri
Enemy hp
Create a live stamina bar | 2024-07-13 | 2024-07-13 | bar: Holidays ¦ July 8th 13 Sat
Stamina
Turn-based Combat
Get mouse input from user | 2024-07-05 | 2024-07-05 | bar: Holidays ¦ July 1st 5 Fri to Holidays ¦ July 1st 6 Sat
Mouse input
Create attack buttons | 2024-07-05 | 2024-07-07 | bar: Holidays ¦ July 1st 5 Fri to Holidays ¦ July 1st 7 Sun
Buttons
Successfully kill enemy | 2024-07-05 | 2024-07-05 | bar: Holidays ¦ July 1st 5 Fri
Defeat enemy
Implement turn-based timing | 2024-07-07 | 2024-07-12 | bar: Holidays ¦ July 1st 7 Sun to Holidays ¦ July 8th 14 Sun
Turn-based timing
Create different attacks | 2024-07-07 | 2024-07-12 | bar: Holidays ¦ July 1st 7 Sun to Holidays ¦ July 8th 12 Fri
Create different attacks
Class Skills
Make specific skills | 2024-07-21 | 2024-07-22 | bar: Holidays ¦ July 15th 21 Sun to Week 1 ¦ July 22nd 22 Mon
Make skills
Create option to select skills | 2024-07-20 | 2024-07-21 | bar: Holidays ¦ July 15th 20 Sat to Week 1 ¦ July 22nd 22 Mon
Selection
Use skills successfully | 2024-07-21 | 2024-07-22 | bar: Holidays ¦ July 15th 21 Sun to Week 1 ¦ July 22nd 22 Mon
Use
Levelling and Progression
Increment player level count | 2024-07-13 | 2024-07-13 | bar: Holidays ¦ July 8th 13 Sat
Level
Increase experience after battle | 2024-07-13 | 2024-07-13 | bar: Holidays ¦ July 8th 13 Sat
XP
Improve character ability stats | 2024-07-13 | 2024-07-13 | bar: Holidays ¦ July 8th 13 Sat
Buff stats
World and Levels
Draw different worlds | 2024-07-23 | 2024-07-23 | bar: Week 1 ¦ July 22nd 23 Tues to Week 1 ¦ July 22nd 25 Thur
Draw
Increment wave count | 2024-07-12 | 2024-07-12 | bar: Holidays ¦ July 8th 12 Fri to Holidays ¦ July 8th 13 Sat
Wave count